## Sheet1
Time Period | Phase | Hours | Hours Spent | Progress | Helper
Week 1 | Concept | 40 | 40 | 100% | 0
Week 2 | Planning | 25 | 25 | 100% | 0
Week 3 | Implementation | 20 | 20 | 100% | 0
Week 4 | Optimization | 15 | 13 | 86.67% | 0
Week 5 | Execution | 50 | 23 | 46% | 0
Week 6 | Verification | 40 | 8 | 20% | 0
Week 7 | Completion | 35 | 0 | 0% | 0
Week 8 | Review | 25 | 0 | 0% | 0